## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Pankaj | 2026-08-25 | Backend dependencies were kept at the wrong project level, making the setup structure unclear. | Sprint 1 | Pankaj | Maintainability | Moved the Python requirements file under the backend module. | 2026-08-25 | Closed | Fresh setup was checked from the backend directory and the dependency file was found in the expected location.
2 | Pankaj | 2026-08-26 | Environment configuration in the README did not fully match the application setup. | Sprint 1 | Pankaj | Standards | Updated the environment documentation and removed unused loader imports. | 2026-08-26 | Closed | The documented variables were rechecked against the backend configuration and the loader remained clean.
3 | Pankaj | 2026-08-27 | Document loading needed a consistent path for different file formats. | Sprint 1 | Pankaj | Logical | Standardized document loading through the Docling-based loader. | 2026-08-27 | Closed | PDF, Office, CSV, and text handling were checked through the shared loader path.
4 | Pankaj | 2026-08-28 | The project document flow was difficult to follow while upload and analysis were being wired together. | Sprint 1 | Pankaj | Logical | Separated project creation from document processing and analysis stages. | 2026-08-28 | Closed | The flow was run end to end from project creation through upload, indexing, and analysis.
5 | Pankaj | 2026-08-29 | The frontend structure needed clearer navigation for project information and analysis results. | Sprint 1 | Pankaj | User Interface | Added a sidebar and reorganized the project views. | 2026-08-29 | Closed | The main project views were opened from the new navigation and routing was checked.
6 | Pankaj | 2026-08-30 | Empty or unreadable document content could interrupt the processing flow. | Sprint 1 | Pankaj | Logical | Added failure handling for missing loader output and zero generated chunks. | 2026-08-30 | Closed | Empty and unreadable document paths were exercised and failure status was recorded without crashing the flow.
7 | Pankaj | 2026-08-31 | Document chunking needed predictable limits and overlap for reliable retrieval. | Sprint 1 | Pankaj | Logical | Configured recursive chunking with explicit size and overlap settings. | 2026-08-31 | Closed | Chunking tests confirmed bounded chunks, overlap behavior, and preserved source metadata.
8 | Pankaj | 2026-09-01 | The analysis flow could regenerate artifacts that were already available. | Sprint 1 | Pankaj | Logical | Added document audit and conditional generation routing. | 2026-09-01 | Closed | A missing-document case routed to generation, while a complete document set skipped the generation step.
9 | Pankaj | 2026-09-02 | Project results also needed to remain searchable after analysis. | Sprint 1 | Pankaj | Logical | Synced the analysis summary and generated-document chunks into Qdrant. | 2026-09-02 | Closed | Generated artifacts were indexed and then retrieved through the project-specific vector store.
10 | Pankaj | 2026-09-03 | Chat results needed clearer source labels for original files and generated content. | Sprint 1 | Pankaj | User Interface | Added source-kind metadata and human-readable source labels. | 2026-09-03 | Closed | Chat helper checks returned the expected labels for regular, generated, and analysis-report sources.
11 | Pankaj | 2026-09-04 | The analysis status did not provide enough visibility while the pipeline was running. | Sprint 1 | Pankaj | User Interface | Exposed pipeline status and current step information to the frontend. | 2026-09-04 | Closed | The analysis flow was followed from running status to completion or failure and the displayed state matched the pipeline.
12 | Pankaj | 2026-09-05 | Project health needed repeatable results across different scope and risk conditions. | Sprint 1 | Pankaj | Logical | Implemented deterministic four-pillar health scoring. | 2026-09-05 | Closed | Boundary cases for empty scope, complete scope, mixed severity risks, and schedule risks matched the expected score behavior.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others